## D18
No. | Quality Metric | Target | Achievement | Month | Year
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | February | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | February | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | February | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | February | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | February | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | February | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | N/A | February | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | N/A | February | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | February | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | February | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | February | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0% | February | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | February | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | February | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | February | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0% | February | 2024
9 | RFI Performance Rate | <10% | 2% | February | 2024
10 | Number of NDT Report Overdue | <3% | N/A | February | 2024
11 | Number of inspection Report Overdue | <5% | 0% | February | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | March | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | March | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | March | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | March | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | March | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | March | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | N/A | March | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | N/A | March | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | March | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | March | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | March | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0% | March | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | March | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | March | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | March | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0% | March | 2024
9 | RFI Performance Rate | <10% | 2% | March | 2024
10 | Number of NDT Report Overdue | <3% | N/A | March | 2024
11 | Number of inspection Report Overdue | <5% | 0% | March | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | April | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | April | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | April | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | April | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | April | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | April | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | N/A | April | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | N/A | April | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | April | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | April | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | April | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0% | April | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | April | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | April | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | April | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0% | April | 2024
9 | RFI Performance Rate | <10% | 2% | April | 2024
10 | Number of NDT Report Overdue | <3% | N/A | April | 2024
11 | Number of inspection Report Overdue | <5% | 0% | April | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | May | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | May | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | May | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | May | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | May | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | May | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | N/A | May | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | N/A | May | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | May | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | May | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | May | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0% | May | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | May | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | May | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | May | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0% | May | 2024
9 | RFI Performance Rate | <10% | 2% | May | 2024
10 | Number of NDT Report Overdue | <3% | N/A | May | 2024
11 | Number of inspection Report Overdue | <5% | 0% | May | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | June | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | June | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | June | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | June | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | June | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | June | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | N/A | June | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | N/A | June | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | N/A | June | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | June | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0.09% | June | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.07% | June | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0.009% | June | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | June | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | June | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0% | June | 2024
9 | RFI Performance Rate | <10% | 5.83% | June | 2024
10 | Number of NDT Report Overdue | <3% | N/A | June | 2024
11 | Number of inspection Report Overdue | <5% | 0% | June | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | July | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | July | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | July | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | July | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | July | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | July | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | N/A | July | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | N/A | July | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | N/A | July | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | July | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0.09% | July | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.07% | July | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0.009% | July | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | July | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | July | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0% | July | 2024
9 | RFI Performance Rate | <10% | 5.83% | July | 2024
10 | Number of NDT Report Overdue | <3% | N/A | July | 2024
11 | Number of inspection Report Overdue | <5% | 0% | July | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | August | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | August | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | August | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | August | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | August | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | August | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | N/A | August | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | N/A | August | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | N/A | August | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | August | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0.09% | August | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.07% | August | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0.009% | August | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | August | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | August | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0% | August | 2024
9 | RFI Performance Rate | <10% | 5.83% | August | 2024
10 | Number of NDT Report Overdue | <3% | N/A | August | 2024
11 | Number of inspection Report Overdue | <5% | 0% | August | 2024

## Petronas
No. | Quality Metric | Target | Achievement | Month | Year
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | April | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | April | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | April | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | April | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | April | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 100% | April | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 0.39% | April | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | April | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | April | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | April | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | April | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0% | April | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | April | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | April | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | April | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.031% | April | 2024
9 | RFI Performance Rate | <10% | 0.565% | April | 2024
10 | Number of NDT Report Overdue | <3% | 0% | April | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | May | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | May | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | May | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | May | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | May | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 100% | May | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 38.7% | May | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | May | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | May | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | May | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0.3% | May | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.01% | May | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | May | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | May | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | May | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.031% | May | 2024
9 | RFI Performance Rate | <10% | 0.73% | May | 2024
10 | Number of NDT Report Overdue | <3% | 0% | May | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | June | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | June | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | June | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | June | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | June | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | June | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 0% | June | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | June | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | June | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | June | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | June | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0% | June | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | June | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | June | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | June | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.001% | June | 2024
9 | RFI Performance Rate | <10% | 0% | June | 2024
10 | Number of NDT Report Overdue | <3% | 0% | June | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | July | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | July | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | July | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | July | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | July | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 25% | July | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 38.7% | July | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | July | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | July | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 8.19% | July | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0.68% | July | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.1% | July | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | July | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | July | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | July | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.021% | July | 2024
9 | RFI Performance Rate | <10% | 20.64% | July | 2024
10 | Number of NDT Report Overdue | <3% | 0% | July | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | August | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | August | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | August | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | August | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | August | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 20% | August | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 38.7% | August | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | August | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | August | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 8.19% | August | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0.63% | August | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.09% | August | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | August | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | August | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | August | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.021% | August | 2024
9 | RFI Performance Rate | <10% | 19.21% | August | 2024
10 | Number of NDT Report Overdue | <3% | 0% | August | 2024

## Shell
No. | Quality Metric | Target | Achievement | Month | Year
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | June | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | June | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | June | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | June | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | June | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | June | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 0% | June | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | June | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | June | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | June | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | June | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0% | June | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | June | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | June | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | June | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.001% | June | 2024
9 | RFI Performance Rate | <10% | 0% | June | 2024
10 | Number of NDT Report Overdue | <3% | 0% | June | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | July | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | July | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | July | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | July | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | July | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | July | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 0% | July | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | July | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | July | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | July | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | July | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0% | July | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | July | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | July | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | July | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.001% | July | 2024
9 | RFI Performance Rate | <10% | 26.67% | July | 2024
10 | Number of NDT Report Overdue | <3% | 0% | July | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | August | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | August | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | August | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | August | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | August | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | August | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 0% | August | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | August | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | August | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | August | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | August | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0% | August | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | August | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | August | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | August | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.001% | August | 2024
9 | RFI Performance Rate | <10% | 20% | August | 2024
10 | Number of NDT Report Overdue | <3% | 0% | August | 2024

## Exxon
No. | Quality Metric | Target | Achievement | Month | Year
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | January | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | January | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | January | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | January | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | January | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | January | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 0% | January | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | January | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | January | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | January | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 1.11% | January | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.22% | January | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | January | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | January | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | January | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.16% | January | 2024
9 | RFI Performance Rate | <10% | 2.29% | January | 2024
10 | Number of NDT Report Overdue | <3% | 0% | January | 2024
11 | Number of inspection Report Overdue | <5% | 0% | January | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | #ERROR! | February | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | #ERROR! | February | 2024
1 | PMT External Audit – Schedule compliance | 100% | #ERROR! | February | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | #ERROR! | February | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | #ERROR! | February | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | #ERROR! | February | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | #ERROR! | February | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | #ERROR! | February | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | #ERROR! | February | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | #ERROR! | February | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | #ERROR! | February | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | #ERROR! | February | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | #ERROR! | February | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | #ERROR! | February | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | #ERROR! | February | 2024
8 | Material Receiving Rejection Rate on Site | <3% | #ERROR! | February | 2024
9 | RFI Performance Rate | <10% | #ERROR! | February | 2024
10 | Number of NDT Report Overdue | <3% | #ERROR! | February | 2024
11 | Number of inspection Report Overdue | <5% | #ERROR! | February | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | March | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | March | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | March | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | March | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | March | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | March | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 0% | March | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | March | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | March | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | March | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 1.85% | March | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.16% | March | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | March | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | March | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | March | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.16% | March | 2024
9 | RFI Performance Rate | <10% | 0.02% | March | 2024
10 | Number of NDT Report Overdue | <3% | 0% | March | 2024
11 | Number of inspection Report Overdue | <5% | 0% | March | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | April | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | April | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | April | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | April | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | April | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | April | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 0% | April | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | April | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | April | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | April | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 1.85% | April | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.16% | April | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | April | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | April | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | April | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.16% | April | 2024
9 | RFI Performance Rate | <10% | 1.97% | April | 2024
10 | Number of NDT Report Overdue | <3% | 0% | April | 2024
11 | Number of inspection Report Overdue | <5% | 0% | April | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | May | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | May | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | May | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | May | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | May | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | May | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 0% | May | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | May | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | May | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | May | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 1.85% | May | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.16% | May | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | May | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | May | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | May | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.16% | May | 2024
9 | RFI Performance Rate | <10% | 1.97% | May | 2024
10 | Number of NDT Report Overdue | <3% | 0% | May | 2024
11 | Number of inspection Report Overdue | <5% | 0% | May | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | June | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | June | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | June | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | June | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | June | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | June | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 0% | June | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | June | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | June | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | June | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0.01% | June | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.02% | June | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | June | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | June | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | June | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.16% | June | 2024
9 | RFI Performance Rate | <10% | 1.36% | June | 2024
10 | Number of NDT Report Overdue | <3% | 0% | June | 2024
11 | Number of inspection Report Overdue | <5% | 0% | June | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | July | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | July | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | July | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | July | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | July | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | July | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 0% | July | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | July | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | July | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | July | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 2.06% | July | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.02% | July | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | July | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | July | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | July | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.16% | July | 2024
9 | RFI Performance Rate | <10% | 1.36% | July | 2024
10 | Number of NDT Report Overdue | <3% | 0% | July | 2024
11 | Number of inspection Report Overdue | <5% | 0% | July | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | August | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | August | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | August | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | August | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | August | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | August | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 0% | August | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | August | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | August | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | August | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 2.41% | August | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.02% | August | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | August | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | N/A | August | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | N/A | August | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.13% | August | 2024
9 | RFI Performance Rate | <10% | 0.68% | August | 2024
10 | Number of NDT Report Overdue | <3% | 0.46% | August | 2024
11 | Number of inspection Report Overdue | <5% | 0% | August | 2024

## BP Petroleum
No. | Quality Metric | Target | Achievement | Month | Year
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | January | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | January | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | January | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | January | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | January | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | January | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 4.81% | January | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | January | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | January | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | January | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | January | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.00% | January | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | January | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | 0% | January | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | 0% | January | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.0002% | January | 2024
9 | RFI Performance Rate | <10% | 0% | January | 2024
10 | Number of NDT Report Overdue | <3% | 0% | January | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | February | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | February | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | February | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | February | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | February | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | February | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 4.81% | February | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | February | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | February | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | February | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | February | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.00% | February | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | February | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | 0% | February | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | 0% | February | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.0002% | February | 2024
9 | RFI Performance Rate | <10% | 0% | February | 2024
10 | Number of NDT Report Overdue | <3% | 0% | February | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | March | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | March | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | March | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | March | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | March | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | March | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 4.81% | March | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | March | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | March | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | March | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | March | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.00% | March | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | March | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | 0% | March | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | 0% | March | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.0002% | March | 2024
9 | RFI Performance Rate | <10% | 0% | March | 2024
10 | Number of NDT Report Overdue | <3% | 0% | March | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | April | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | April | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | April | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | April | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | April | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | April | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 4.81% | April | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | April | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | April | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | April | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | April | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.00% | April | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | April | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | 0% | April | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | 0% | April | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.0002% | April | 2024
9 | RFI Performance Rate | <10% | 0% | April | 2024
10 | Number of NDT Report Overdue | <3% | 0% | April | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | May | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | May | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | May | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | May | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | May | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | May | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 4.81% | May | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | May | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | May | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | May | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | May | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.00% | May | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | May | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | 0% | May | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | 0% | May | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.0002% | May | 2024
9 | RFI Performance Rate | <10% | 0% | May | 2024
10 | Number of NDT Report Overdue | <3% | 0% | May | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | June | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | June | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | June | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | June | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | June | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | June | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 4.81% | June | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | June | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | June | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | June | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | June | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.00% | June | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | June | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | 0% | June | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | 0% | June | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.0002% | June | 2024
9 | RFI Performance Rate | <10% | 0% | June | 2024
10 | Number of NDT Report Overdue | <3% | 0% | June | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | July | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | July | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | July | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | July | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | July | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | July | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 4.81% | July | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | July | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | July | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | July | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | July | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.00% | July | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | July | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | 0% | July | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | 0% | July | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.0002% | July | 2024
9 | RFI Performance Rate | <10% | 0% | July | 2024
10 | Number of NDT Report Overdue | <3% | 0% | July | 2024
1 | PMT Internal Audit – Schedule Compliance | >70% | N/A | August | 2024
1 | PMT Internal Audit – Requirement Compliance | >95% | N/A | August | 2024
1 | PMT External Audit – Schedule compliance | 100% | N/A | August | 2024
1 | Contractor Project Audit (Internal Audit & External Audit) – Schedule Compliance | 100% | 100% | August | 2024
2 | Gaps closure timeliness for all lines of Integrated Assurance findings | 100% | N/A | August | 2024
2 | Overdue closure of NCR (including NCR raised during audit) | <10% | 0% | August | 2024
3 | Engineering Drawing Revision post IFD/IFC | <5% | 4.81% | August | 2024
4 | Design Change resulting in Variation Order (VO) | <5% | 0% | August | 2024
5 | Overdue closure of Major/Critical design related findings | <3% | 0% | August | 2024
6 | FAT/ SAT Reject Rate for Major Equipment | <2% | 0% | August | 2024
7 | Cumulative WRR - Process Piping (measured by joints) | 5% | 0% | August | 2024
7 | Cumulative WRR - Process Piping (measured by linear length) | 0.5% | 0.00% | August | 2024
7 | Cumulative WRR - Structural Steel (measured by linear length) | 1% | 0% | August | 2024
7 | Cumulative WRR - Storage Tanks (measured by linear length) | 1% | 0% | August | 2024
7 | Cumulative WRR - Pipeline (measured by joints) | 5% | 0% | August | 2024
8 | Material Receiving Rejection Rate on Site | <3% | 0.0002% | August | 2024
9 | RFI Performance Rate | <10% | 0% | August | 2024
10 | Number of NDT Report Overdue | <3% | 0% | August | 2024